## Sheet1
| PLANING STAGE |  |  |  |  | DESIGN |  |  |  |  | BUILD |  |  |  |  | LAUNCH
| Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5
Project Manager | Customer Contact and Project management |  |  |  |  | Customer Contact and Project management |  |  |  |  | Customer Contact and Project management |  |  |  |  | Customer Contact and Project management
Content Developer | INITITIAL MEETING
Photographer | [5 empty] | Photoshoots
|  | RESEARCH | STRATEGIC PLANNING
Copywriter | [6 empty] | All Copy for Webpage
Designer | [6 empty] | Style Tiles and Design Elements |  |  |  | Wireframes
Content and Front End Dev | [8 empty] | Initial meetings and direction |  | UI PLANNING AND TESTING
Front End Developer | [12 empty] | CODING AND SITE BUILD
Full Stack Developer | [15 empty] | BACK END STUFF
Whole Team | [17 empty] | Final touches and Customer meeting |  | LAUNCH